## Sheet1
Module | Submodule | Functionality | UI/UX (hrs) | Dev (hrs) | Testing (hrs) | Buffer (hrs) | Total (hrs)
Video Playback | HLS/DASH Streaming | Stream pre-rendered video segments, ABR switching, seamless transitions | 20 | 40 | 20 | 10 | 90
Video Playback | Controls | Mute/unmute, captions, restart, haptics | 10 | 20 | 10 | 5 | 45
Branching Engine | State Machine | Manage nodes, edges, and decision points | 20 | 50 | 20 | 10 | 100
Branching Engine | Preloader | Preload most-likely next segments, fallback handling | 15 | 40 | 15 | 10 | 80
Overlay UI | Decision Overlays | Interactive choices, countdown, auto-advance | 20 | 40 | 15 | 10 | 85
Overlay UI | Accessibility | WCAG 2.1 AA compliance, screen reader support | 15 | 20 | 15 | 10 | 60
AI/NLP | Recommendation Engine | Personalized branching paths | 15 | 60 | 20 | 20 | 115
AI/NLP | Voice/NLP | Voice input, natural language intent recognition | 20 | 70 | 25 | 20 | 135
AI/NLP | Dynamic Narration | TTS voiceover per locale/style | 15 | 50 | 20 | 15 | 100
CMS/Admin | Story Graph Editor | Drag-drop nodes/edges, JSON export | 25 | 60 | 20 | 15 | 120
CMS/Admin | Localization | Multi-language strings & VO management | 20 | 40 | 15 | 10 | 85
Analytics | Event Tracking | video_start, decision_shown, option_selected, etc. | 15 | 40 | 20 | 10 | 85
Analytics | Reporting | Funnels, path analysis, exports to CSV/BigQuery | 20 | 40 | 20 | 10 | 90
CRM Integration | Lead Forms | Form validation, OTP verification | 15 | 40 | 20 | 10 | 85
CRM Integration | API Integration | Salesforce/HubSpot/Marketo connectors | 10 | 40 | 20 | 10 | 80
Security | CDN & Access Control | Signed URLs, WAF, Shield, headers | 5 | 20 | 10 | 5 | 40
Security | Data Privacy | PII encryption, consent management | 10 | 20 | 15 | 5 | 50
Localization & Accessibility | Multi-language | Subtitles, audio tracks per locale | 15 | 30 | 15 | 10 | 70
QA & Testing | Cross-browser & device | Path coverage, throttled networks | 10 | 0 | 40 | 10 | 60
QA & Testing | AI Behavior | Accuracy tests, fallback validation | 10 | 0 | 40 | 15 | 65
Infra & DevOps | CI/CD Setup | Automated pipelines, staging/prod setup | 5 | 30 | 10 | 5 | 50
Infra & DevOps | AWS Infra | S3, CloudFront, Lambda, DynamoDB setup | 5 | 40 | 15 | 10 | 70